## Sheet1
Day | Phase | Task | Owner | Status
0 | Prep | Sign LOI & pay deposit | You | ☐
1 | Prep | Engage franchise attorney | You | ☐
3 | Prep | Review FDD 2025, highlight red flags | Lawyer | ☐
7 | Prep | Apply for EIN & business bank | You | ☐
10 | Prep | Order site-demographics report (Heatmapfy) | HQ | ☐
14 | Lease | Short-list 5 high-traffic locations | You | ☐
18 | Lease | Contact property managers for LOIs | You | ☐
25 | Lease | Negotiate radius protection (≥ 3 mi) | Lawyer | ☐
30 | Lease | Sign final location agreement | You | ☐
35 | Finance | Choose: cash / equipment loan / 401(k) | You | ☐
42 | Finance | Submit funding docs to Balboa Capital | Bank | ☐
49 | Admin | File state sales-tax permit | You | ☐
52 | Admin | Buy general & product-liability insurance | Broker | ☐
56 | Build | Pay starter package invoice ($29.9 k) | You | ☐
63 | Build | Receive machine – inspect serial # | You | ☐
70 | Build | Install telemetry tablet & test remote | HQ IT | ☐
77 | Build | Stock initial inventory (220 SKUs) | You | ☐
84 | Marketing | Create Google Business profile | You | ☐
88 | Marketing | Print “Grand Opening” posters | HQ | ☐
91 | Training | Attend 2-day Vegas training + ANSI exam | You | ☐
98 | Training | Upload brand-approved social posts | You | ☐
105 | Soft-Open | Place machine on site (dolly + straps) | You | ☐
107 | Soft-Open | Run 48-hr continuous test (sales + telemetry) | You | ☐
110 | Soft-Open | Adjust top-5 SKUs by sell-through | You | ☐
115 | Final | Schedule first refill route in calendar | You | ☐
118 | Final | Send opening press-release to local Patch | HQ | ☐
120 | Launch | Official GO LIVE – monitor hourly sales | You | ☐