## Sheet1
Task | Start Day | End Day | Duration | Week | Critical Path
Sign FDD | 1 | 3 | 3 | Week 1 | Yes
Wire Initial Fee | 2 | 2 | 1 | Week 1 | Yes
Open Business Bank Account | 3 | 4 | 2 | Week 1 | Yes
Engage Franchise Attorney | 3 | 5 | 3 | Week 1 | No
Order Background Checks | 4 | 7 | 4 | Week 1 | Yes
Create LLC / Corporation | 4 | 6 | 3 | Week 1 | No
Apply for EIN | 5 | 5 | 1 | Week 1 | No
Prepare SBA Package | 5 | 14 | 10 | Week 1-2 | Yes
Submit SBA to Bank | 8 | 8 | 1 | Week 2 | Yes
Site Selection Kick-off | 8 | 21 | 14 | Week 2-3 | No
Receive SBA Pre-Qual Letter | 9 | 11 | 3 | Week 2 | Yes
Sign LOI on Premises | 10 | 12 | 3 | Week 2 | Yes
Landlord Delivery Checklist | 13 | 15 | 3 | Week 2 | No
Order Demographics Study | 13 | 20 | 8 | Week 2-3 | No
Landlord Lease Draft Review | 16 | 19 | 4 | Week 3 | No
Final Lease Execution | 20 | 20 | 1 | Week 3 | Yes
File DBA / Trade Name | 21 | 21 | 1 | Week 3 | No
Apply for Business License | 21 | 28 | 8 | Week 3-4 | Yes
Submit Plans to City | 22 | 29 | 8 | Week 3-4 | Yes
Order Equipment Package | 23 | 25 | 3 | Week 3 | Yes
Open Business Insurance | 24 | 24 | 1 | Week 3 | No
Landlord Build-Out Start | 30 | 44 | 15 | Week 4-6 | Yes
Receive SBA Loan Commitment | 26 | 28 | 3 | Week 4 | Yes
Wire SBA Down-Payment | 29 | 29 | 1 | Week 4 | Yes
Hire General Contractor | 31 | 31 | 1 | Week 5 | No
Schedule Final Inspections | 40 | 42 | 3 | Week 6 | Yes
Order POS System | 32 | 34 | 3 | Week 5 | No
Order Opening Inventory | 35 | 37 | 3 | Week 5 | No
Create Local Marketing Plan | 36 | 38 | 3 | Week 5 | No
Design Grand Opening Flyers | 39 | 41 | 3 | Week 6 | No
City Fire Inspection | 43 | 43 | 1 | Week 6 | Yes
City Health Inspection (if food) | 44 | 44 | 1 | Week 6 | Yes
Build-Out Punch List | 45 | 46 | 2 | Week 6 | No
Install Exterior Signage | 47 | 48 | 2 | Week 7 | No
POS Training | 49 | 49 | 1 | Week 7 | No
Staff Job Posting | 38 | 45 | 8 | Week 5-6 | No
Interview Candidates | 46 | 50 | 5 | Week 7 | No
Background & Drug Tests | 51 | 53 | 3 | Week 7 | No
Staff Offer Letters | 54 | 54 | 1 | Week 7 | No
Staff Paperwork & Uniforms | 55 | 55 | 1 | Week 8 | No
Franchise HQ Training | 50 | 54 | 5 | Week 7-8 | Yes
Final Inventory Delivery | 56 | 56 | 1 | Week 8 | No
Soft-Opening (Friends & Family) | 57 | 57 | 1 | Week 8 | No
Soft-Opening Feedback Fix | 58 | 58 | 1 | Week 8 | No
Local Influencer Preview | 59 | 59 | 1 | Week 8 | No
Grand Opening Day | 63 | 63 | 1 | Week 9 | Yes
Grand Opening Campaign | 60 | 63 | 4 | Week 9 | No
First Payroll Run | 64 | 64 | 1 | Week 9 | No
Review 7-Day P&L | 65 | 65 | 1 | Week 9 | No